Biofuels Team

Transportation for the Future Initiative

Western Governors Association

May 14-15, 2007

Attendees:							WGA & Project Staff:

Alan Weverstad		Paul Wuebben			Gayle Gordon

David Terry			Kourtnie Harris		Will Singleton

Charles Bensinger		Vance Kopp			John Brenner

On the Phone and Partial Attendees:

Alex Schroeder- WGA	Heather Bergman- TKC

Meeting Objectives:

- Clarify the charge of the group, decision-making, and leadership with a clear plan for drafting the report over the coming two months;

- Discuss short-term recommendations (that governors should pursue in the coming weeks)

- Focus on barriers and recommendations as a way to establish the appropriate format for the paper.

Agreements:

- The protocols were accepted as written and shall be used as a guideline for the team’s interactions and decision-making;

Action Items:

| Who | What | When |
| --- | --- | --- |
| Whole Team | Send Gayle recommendations for Farm Bill and other key suggestions that are time sensitive (June) | As soon as possible |
| Gayle | Copy of members of the advisory committee to the team members. | As soon as feasible |
| Gayle | Send info on WGA Biofuels Initiative to the team |  |
| Paul and David | look at GEC Report to see how it can add to the Biofuels paper |  |
| Gayle and David and full team | Review recommendations/ letter to go out in 10 days | Feedback by 5/24 noon |

The Charge of the Group:

Gayle reported on the Advisory Committee meeting in April and helped to lay out the purpose of the paper. The initiative is derived from an interest among the governors to: 1). Reduce reliance on imported fuels; 2). Minimize negative environmental impacts, including carbon emissions; 3). Provide the western states with a full palette of energy options for transportation.

The review of the outline shows the major emphasis of the papers. Because of the short timeline, many of the sections will need to build on reports that have already been done. The key emphasis will be on the recommendations to the governors. The major sections are:

- Description of the Alternative Fuel

- Potential Supply, Technology Progression and Markets in Western States

- Predicted Deployment/ Timeline

- Barriers & Challenges

- Life-Cycle Environmental & Societal Impacts

- Synergies with Other Fuels

- Recommendations at the State, Regional, and Federal Levels

- Demonstration Projects

A review of the protocols emphasized that the effort would need to be collaborative. A key value of the report will be the weight of the list of authors. The protocols that were accepted emphasized that decision-making by consensus means that broad agreement (but not absolute) should be reached. Participants should measure whether they can live with the “big picture” rather than focusing on potential details that they don’t agree with.

The timeline is to have a viable draft of each section by July 1 so that a draft can be posted on the web and sent to the Advisory Committee by July 15th. The Advisory Committee will have an opportunity to comment, but each team has the ability to determine the final contentof its own report. The Advisory Committee will seek to identify synergies and key recommendations that it will pass on in its report to the governors.

Operational Highlights:

The team discussed some of the logistics of how it would operate. Operational details follow, including roles, timeline and paper length:

Team: Team members are responsible for drafting the report through their own original work and through identifying existing work that can be included in the report. Team members will be identified as authors on the final report.

Chair: Will help represent the views of the team in drafting agendas and the broader program. Will oversee the engagement of team members in drafting the report. Will represent the team to the Advisory Committee as appropriate.

WGA: To assist as the convener with advice on how to maximize the effectiveness of the report in the context of Western Governors and the larger initiative. WGA named the teams and is also responsible for the logistical needs of the team as appropriate.

TKC: Will draft agendas, summaries and assist in the final formatting/ editing of the report. TKC will facilitate meetings and conference calls as needed and help to address disagreement if necessary.

The WGA has a concurrent project that is working to compile data that will be helpful to several sections of the paper. The Biofuels Research Initiative – headed by Richard Nelson – will be working to develop information on supply sources, technology and technology progression and predicted deployment and conversion technologies. While the initiative is not expected to be complete until the end of the summer. Some information will be ready in draft form beginning in June.

Timeline:	July 1, draft sections complete

July 15th- Draft for public/ Ad Com

Sep/August- Revision/ finalize

October- Workshop

Organization of the Paper:

Length 25-30 pages-	5 for benefits

5 for challenges

7-8 for recommendations

2 for others

Paper Production: The team reviewed the main sections of the paper and volunteered to help compile the sections. Section leads are in bold. Those not present are in italics. They were identified as potential contributors based on their expertise.

|  | Who | Date | Special Instructions |
| --- | --- | --- | --- |
| Potential & Benefits | NREL- Charles- feedstock, Phil- E-85 | July 1st, completed draft sections | - This section to include definitions? - DOE Roadmap, butonol - Technologies & feedstocks - No chicken & egg problem - Corn & celluostic - What feedstock works where - USFS- feedstock - Get the number of FFVs/ state |
| Barriers & Challenges | David, Charles, Phil | July 1st, completed draft sections | - Look at DOE produced list of barriers. - David can work on deployment |
| Lifecycle/ Enviro. | John Brenner, Matt (intern) | July 1st, completed draft sections | - Base approach on GREET model - NREL to give data on tail pipe emissions and plant |
| Demonstrations | Kourtnie, Paul, Charles, David |  | - Kourtnie to work on regional demonstrations - Collection/pretreatment/ conversion - 3 best celluostic sites in the US |
| Recommendations | David, with assistance from all | July 1st, completed draft sections | Recommendations should include state, regional, and federal levels - DOE has a good incentive table |

Resources for the Life-Cycle and Environmental Impacts Section: The expectation that much of the data intense analysis of life cycle impacts will be done on behalf of all the teams so that the same metrics can be used for all. John Brenner volunteered to write the remaining piece of the analysis to meet Advisory Committee needs. The team suggested several sources of information to help with the process. They included the work of Mark Deluci, Alex Farrell and Dan Kamen. For land and water impacts potential good sources of information include: Nathaniel Green at NRDC, Bruce Dale at the Great Plains Institute, the Rocky Mountain Institute, Oakridge (specifically on land-use) and Richard Nelson. GM is also a strong potential source of information.

For lifecycle impacts, WGA is considering using the GREET Model because it considers all fuels as a generic model and then applies to independent states but the analysis would need state specific greet with benchmarking and tracking.

The group agreed that John should write a short section on corn and then address the potential impact of a broader range of feedstocks. The implications of utilizing CRP lands should also be addressed.

Discussion:

Special Conditions in the West: The differentiating quality of the paper for tins initiative as opposed to other efforts is that it will need to consider the special aspects of the western states will assist or hinder the broad use of biofuels. Some of the special qualities of the West include:

- There is a small amount of corn grown west of the Rocky Mountains, most of it is grown east of the 100th Meridian, SD, NE, KA, OK, etc

- Irrigation impacts the production of feedstock

- Continued pressure on corn prices means oil import price vulnerability

- There is a diversity of potential feedstock in the West that is not yet utilized

- There is private sector (venture capital) leadership in the West

- Logistics are more difficult in the West because of problems with transporting feedstock

- If strategic planning is done, use and production can work together. Ethanol can be distributed to serve a distributed market –especially celluostic. This would mean important cost cutting in transportation.

- Feedstock residues can be used for the livestock industry (distillers grain)

- The only way you get to celluostic ethanol (that is move ethanol to much broader use as a fuel) is for the West to succeed in supplying feedstock

- The West is unique to provide E-85 beyond corn. Delivering it is a problem. It can be made here which could mean less transportation / costs / through trucking.

- We have a vulnerability to climate change here.

- Poor infrastructure in Interior West

Benefits and Potential: This first section of the paper is important because it will set the context for challenges and recommendations. This section is intended to cover the likely progression of technology and infrastructure as the fuel becomes more widely used. It also intended to highlight the benefits and some policy drivers of the resource. Some of the key points of the discussion were:

Benefits:

- Ethanol teaches people to look beyond petroleum to other options

- FFV is an agile technology that can be applied with many alternative fuels

Potential:

- DoE has issued a report- 39% of fuel use can be ethanol, 31% celluostic, 8% corn based

- 140 billion gallons by 2012 may hit corn constraint

Infrastructure and Technology Deployment:

- Is there a volume threshold for a pipeline?

- The Governors’ Ethanol Coalition has sought to look at this

- In the short-term, truck it

- Medium-term, rail, truck, pipeline (10-15 billion gallons / year)

- Long-term, multi feedstock, biodiverse, distributed production & use

- Future demand scenarios depending on certain breakthroughs

- Where are the terminals that will accept ethanol?

- Unlike many other alternative fuels, there is infrastructure at the consumer level.

- E-10 will open up demand. Early FFV expedited deployment and their requirements– 10% with conventional ethanol

- Rising prices need to bring celluosic production. Bruce Dale’s paper talks about celluosic costs at $1.25 / gallon

  - Colorado has 20 branded stations. The prices are always lower.

  - The blend market currently is more profitable than E-85. It won’t be in 3-5 years.

Barriers and Challenges: Partly to identify major challenges to be discussed in the paper but also as a preface for recommendation, the team discussed the major challenges and barriers that biofuels face as the resource moves towards its full potential.

Economics:

- Price elasticity- do we really know what more supply is going to do to prices?

- Resource currently competes with food production. Food vs. Fuel- Lack of due diligence tracking on corn viability

- Over supply of corn lowers prices for all ethanol- are we vulnerable to boom and bust?

- Lack of capitol for gasification technologies. Venture capital is reluctant to make increased investments. How to address the “valley of death” problem. How to invest in Unit #1.

  - The technology makes the fuel too expensive

- Resource may be too distant and transportation of resource may be too costly to make economics feasible.

- Need more stations- Capital to build the stations

- We still need to solve model for high through-put

Regulations:

- California emissions standards- E-10 and PZEVs, pure E-85 cold start test

  - GM will limit E-85 vehicles in CA

  - They are hoping that direct injection will make cold start work—2010s

- Underwriters Labratories will not certify E-85 tanks

- California regulations prevent infrastructure change at stations

- There is currently insufficient end use data. Industry needs to assure acid aldahide levels to maximum air quality benefit. There is no current standard. There is fear of unintended consequences.

Environment:

- Poor understanding of true comprehensive environmental impacts (land, water) with validation and auditing, federal/state coordination and funding.

Feedstock Supply:

- For celluosic, there is a lack of science to produce the needed diversity of enzymes.

Industry/ Commercialization:

- Prohibitions of major companies of non-branded fuels under their canopies at stations prevents easy access

- E-85 has to be away from other fuels to ensure that there is no use by inappropriate consumers.

- Consumer knowledge is low.

- Inconsistent quality standards with independent marketers/producers

Recommendations: The team discussed two separate sets of recommendations. The first set was recommendations that need to be forwarded to the Advisory Committee almost immediately if they are to be relevant (such as the Farm Bill which is being considered by Congress in the very near term). The second set was the recommendations that will help biofuels overcome barriers to achieve full market penetration. The team will need to weed out recommendations that are not actionable by governors.

Short Term Recommendations: The team discussed the Governors’ Ethanol Coalition report and recommendations. It was agreed that the report serves as a good basis for recommendations by WGA governors. There is a very strong geographic overlap and the GEC has had an exhaustive process in developing the recommendations.

Farm Bill

- Governor’s Ethanol Coalition recommendations for the Farm Bill

- Everyone should read it and refer their preferred recommendations

- Conversion of feedstock- Tried to Identify

- Establish a crop program- growing other crops to allow farmers to gain knowledge

- Cost sharing for equipment

- Governors should be encouraged to adopt the Colorado model for the UL issue- not certifying EQ for E-85 tanks. Fire marshals / install with certification from manufacturers to address corrosion and vapor pressure.

- ARPA-E- House Science Committee – possible consideration by full House in June

- Governors should advocate for Biomass R&D at the USDA that gets at the feedstock questions, fund the full $12,000,000 authorized amount

- Governors should advocate that Section 942 of EPAct incentive for corn-based ethanol production, be funded through the USDA

- Sun Grant Initiative – Governors should advocate for reauthorization

- Conservation Reserve Program – consider land conversion for growing of energy crops

- Crop insurance- extend rules to new crops

House Energy & Water Appropriations

- EERE funding ($251 million- full authorized amount)

- Tweak funding for infrastructure- $10-25 to be targeted to competitive technologies

  - Funding Clean Cities program – at a low level

- Loan guarantee program through the USDA for low carbon fuels, need debt subjugation- feds need to do full guarantee

- Soil Quality Modeling- how much vegetation can you take off the land?

- Co-Products Demonstrations

Report Recommendations: The team reviewed its discussion of barriers and suggested the following list of potential recommendations. Some recommendations are more actionable by governors.

- Advocate price guarantee for celluostic production

- Gain broad adoption of biofuels in state renewable fuel standards

- Advocate for a loan guarantee program that will address the “valley of death” stage for gasification that is between R&D and commercialization

- Utilize B-20 B-2 Standards to address cold start issues with E-85

- Conduct state by state resource inventory of feedstock. Include the states in the process so that they can add their own information.

- Advocate for significant Department of Energy for the West with a focus on diverse conversion techniques such as: PKE Treatment, Enzymes

- Optimize regulations tailored competition (through and RfP?) to develop 5-10 million gallons to scale in 10-15 years, ultimately increase to 50 million gallons

- Unveil a multi-state station/vehicle roll-out: propose x% vehicle sales of flex-fuel vehicles and x% stations as E-85 compatible

- Set state and regulatory goals for % of E-85 volumes by state

- For infrastructure development, address barriers in siting of storage/distribution, help with retail burden-sharing (per gallon incentive) by proposing a subsidy higher than $.51, and establish E-85 Interstate corridors. This could be the nation’s first regional/multi-state coordinated infrastructure plan.

- Establish a regional ethanol reserve—to maintain some amount of supply a month

- Use government funds to implement producer short and medium term burden sharing combined with gross receipt tax elimination

- Help establish some income streams with long-term celluostic ethanol supply contracts for federal & state purchases

- State government tax incentives and tax credit or grants for station/ infrastructure and feedstock processes

- Incentives for municipalities to buy ethanol friendly fleets

- Combined heat and power digester- low carbon fuel standard

- Implement a program to increase understanding of true comprehensive environmental impacts (land, water) with validation and auditing

- Co-locate renewable energy (wind, solar) with biofuel plants to share transmission and cost

  - Utilize renewable energy as an energy supply for production of biofuels

  - Achieve lower carbon footprint through energy sources other than coal & avoid minimize fossil fuel use.

- Create a national standard – E-10 delivered by a unique nozzle

- Create national ASTM standard

- Create a WGA Fuels office that can integrate and monitor information on biofuels/biomass- Release an RfP to propose different approaches and attract venture capital.

- 1 cent / gallon to invest in transition to renewable fuels. Call it a “sustainable energy transition fee”

- Regional low carbon fuel standard

  - Work to achieve a carbon intensity reduction by a certain state

  - 20% less carbon footprint/lifecycle