Biodiesel & Renewable Diesel Team

Transportation Fuels for the Future Initiative

Western Governors Association

May 21-22, 2007

Draft Meeting Summary

Attendees:							WGA & Project Staff:

Richard Nelson		Kim Lyons			Gayle Gordon

Ed Sughrue			Xiao Lei Sun			John Brenner

Wade Deerman		Bob Mailander		Will Singleton- TKC

Bob McCormick		Lance Lobban			Matt Futch

Vance Kopp			Bryan Willson

Observers:

Meeting Objectives:

- Clarify the charge of the group

- Approve decision-making and structure of the team as described in the protocols

- Develop a section by section work plan for the team report

- Discuss content for the report including potential, barriers and recommendations

Agreements:

- The protocols were adopted as written and shall be used as the guideline for the team’s interactions and decision-making.

Action Items:

- Gayle or Will will contact Renteck about including biomass to liquids as a stream through the paper

- Do a conference call on LCA with Bob McCormick

- John- preprocessing facilities?

The Charge of the Group:

Gayle reported on the Advisory Committee meeting in April and helped to lay out the purpose of the paper. The initiative is derived from an interest among the governors to: 1). Reduce reliance on imported fuels; 2). Minimize negative environmental impacts, including carbon emissions; 3). Provide the western states with a full palette of energy options for transportation.

The review of the outline shows the major emphasis of the papers. Because of the short timeline, many of the sections will need to build on reports that have already been done. The key emphasis will be on the recommendations to the governors. The major sections are:

- Description of the Alternative Fuel

- Potential Supply, Technology Progression and Markets in Western States

- Predicted Deployment/ Timeline

- Barriers & Challenges

- Life-Cycle Environmental & Societal Impacts

- Synergies with Other Fuels

- Recommendations at the State, Regional, and Federal Levels

- Demonstration Projects

A review of the protocols emphasized that the effort would need to be collaborative. A key value of the report will be the weight of the list of authors. The protocols that were accepted emphasized that decision-making by consensus means that broad agreement (but not absolute) should be reached. Participants should measure whether they can live with the “big picture” rather than focusing on potential details that they don’t agree with.

The timeline is to have a viable draft of each section by July 1 so that a draft can be posted on the web and sent to the Advisory Committee by July 15th. The Advisory Committee will have an opportunity to comment, but each team has the ability to determine the final contentof its own report. The Advisory Committee will seek to identify synergies and key recommendations that it will pass on in its report to the governors.

Operational Highlights:

The team discussed some of the logistics of how it would operate. Operational details follow, including roles, timeline and paper length:

Team: Team members are responsible for drafting the report through their own original work and through identifying existing work that can be included in the report. Team members will be identified as authors on the final report.

Chair: Will help represent the views of the team in drafting agendas and the broader program. Will oversee the engagement of team members in drafting the report. Will represent the team to the Advisory Committee as appropriate.

WGA: To assist as the convener with advice on how to maximize the effectiveness of the report in the context of Western Governors and the larger initiative. WGA named the teams and is also responsible for the logistical needs of the team as appropriate.

TKC: Will draft agendas, summaries and assist in the final formatting/ editing of the report. TKC will facilitate meetings and conference calls as needed and help to address disagreement if necessary.

The WGA has a concurrent project that is working to compile data that will be helpful to several sections of the paper. The Biofuels Research Initiative – headed by Richard Nelson – will be working to develop information on supply sources, technology and technology progression and predicted deployment and conversion technologies. While the initiative is not expected to be complete until the end of the summer. Some information will be ready in draft form beginning in June.

Timeline:	July 1, draft sections complete

July 15th- Draft for public/ Ad Com

Sep/August- Revision/ finalize

October- Workshop

Paper Production: The team reviewed the main sections of the paper and volunteered to help compile the sections. Section leads are in bold. Those not present are in italics. They were identified as potential contributors based on their expertise.

| Section | Name | Date | Key Points |
| --- | --- | --- | --- |
| I. Definition (1 page) | Richard Nelson, Ed Shugrue (R.D.), Bryan Willson (algae) | 6/15- Draft 7/1- Final Section |  |
| II. Potential & Benefits (6-7 pages) | Richard Nelson, Kim, Ed, Bryan & Sally, Loren | 6/15- Draft 7/1- Final Section | Loren- growth in diesel Neville Fernandes- growth? Supply sources- Kim Technology- Antares (Ed Grey), Kim Markets- Jeff Probst? Disadvantages of Fuel- Sally among others Oil/Gas Displaced- NREL (Bob?) Current usage. |
| III. Barriers & Challenges (5 pages) | Lance, Bryan & Sally, Ed, John Brennan (feed stock) | 6/15- Draft 7/1- Final Section | Ed has list of problems to be overcome |
| IV. Lifecycle Analysis, Environmental and Societal Impacts (3.5 pages) | Bob McCormick, Bryan Wilson | 6/15- Draft 7/1- Final Section |  |
| VI. State, Regional, and Federal Recommendations (8-10 pages) | Colin, Wade, Kim, Lance, Richard? | 6/15- Draft 7/1- Final Section | ASTM- Bob McCormick |
| Demonstrations | Bryan, Ed, Sally, Lance | 6/15- Draft 7/1- Final Section | Coordinate up and down food chain- Bob Mailander |
| Synergies | Bryan, Ed, Sally, Lance | 6/15- First thoughts 8/1- Final Section | Algae/ethanol/ctl H2 This section will be completed after we have seen recommendations from other teams |

Lifecycle & Environment: The expectation is that much of the data intense analysis of life cycle impacts will be done on behalf of all the teams so that the same metrics can be used for all. Major potential sources of information could be John Sheehan’s 1998 NREL report, Phil Parsons- CSU/NREL report that analyzed both biodiesel and ethanol, a report by Michael Wong- Argonne Laboratories. University of Minnesota has done some important work on lifecycle.

For the report, the biodiesel team should work on a qualitative discussion of environmental and social impacts, in the process some of the following might be considered: land use, water use, air quality and other emissions, soil health, impacts on rural infrastructure, community impact, and environmental justice

Discussion:

Broad Issues: The team articulated some overarching thoughts at the beginning of the meeting. They follow:

- It was proposed that the team might be called “Oils, Fats, and Pond Scum” as a clear way of defining the group.

- The timeline and perhaps organization for the paper should follow along the timeline for the technologies:

Short-term- Conventional

Medium-term- Renewable Diesel

Long-term- Gas to liquid, BTL, Algae

- A major question right now is whether the resource will be provided through a few big plants or many small plants. Big plants may represent the necessary economy of scale to produce at industrial levels. Small plants offer closer access to feedstock and an ability to provide fuels locally.

Benefits, Potential and Deployment: The “Potential” section of the paper is meant to combine substantive reporting on specific questions with an introduction to the resource that will convey the opportunity that biodiesel presents to meet the objectives of the resolution. The following is a summary of the main points of the discussion:

- 9 million gallons/day can be produced nation-wide

- DOE analysis predicts that by 2020, 15% of the fleet will be run on bio or renewable diesel

- Diversity of feedstock can be used that will mean consistent delivery of the resource and a more diverse income stream for growers. Cottonseed can be combined with winter canola.

- Good for rural communities

- Movement towards diversification for energy as well is good for land and rural communities

- Diesel use in passenger vehicles on increase in the US?

  - Conoco Philips wants more diesel use

  - High mileage diesel vs hybrid

- Presentations were made by Ed Sughrue, Xiao Lei Sun, and Bryan Willson on the potential of their emerging approaches to biodiesel:

  - Conoco Phillips has developed a proprietary processing technique that can produce consistent quality “renewable” diesel;

  - Arizona Public Service is implementing innovative programs that use CO2 from power plants to produce biodiesel from algae

  - Colorado State University is working on a second generation algae production unit that will lower capital costs while realizing the land, water and energy efficiency of making biodiesel from algae.

Challenges/Barriers: Partly to identify major challenges to be discussed in the paper but also as a preface for recommendation, the team discussed the major challenges and barriers that biodiesel faces as the resource moves towards its full potential. Potential solutions are in italics.

Biodiesel:

- Economics are tight when oil seed / feedstock is at 25-30 cents / gallon

- The fuel resource is small unless new feedstocks come on line

- Engine manufacturers are reticent to cooperate

- Supply of feedstock- most areas in the West will not support even small plants

- 2010 standards will be difficult for small suppliers to comply

- Diesel use in US is low

- The large distance to plants means that transportation of feedstock is a major cost factor

- Poor fuel quality and capacity for labeling/testing at the state level. B-5

- Uncertainty of legislation- 2% volume in NW NIST

- No kicker to ensure consistent participation among refineries. A few good actors have to make up for the bad ones. Get the weights and measures agencies to recognize the new fuels, establish some standard protocols and provide government funding for testing.

- Wide variability of the fuel (2, 5, 20, 99%) poses a number of problems, they include:

  - 2010 requirements means that NOx has to be decreased

  - Manufacturers cant meet the targets with variability

  - Consumer confusion

    - They know what to buy

    - Warrantees won’t cover variability in fuels

    - Sometimes unclear chain of custody that would show quality accountability

  - Develop an industry consensus based standard- ASTM

- International competition can often provide feedstock more cheaply than domestic sources, growers in the use need 40-50 cents / lb to be able to break even.

  - Lower cost for canola if grown in rotation

- Growers face uncertainty of pricing when working against corn

  - Solidify market for farmers through establishment at Chicago Merc. Exchange or some other l-t market tool

- Subsidy for ethanol perverts economics for biodiesel

- Wide use of canola is difficult because of a lack of knowledge of agronomy, fear of transgenic crop genetic drift, and the competition between food-grade and industrial oils.

- Growers need income from meal to make the economics work but there is a limit to how much meal can be absorbed by the market. 2% biodiesel use in the US market (20,000,000 gallons) would supply 60% of all needed dairy meal.

  - Look for other uses such as pesticides

- Growers need long term guarantees of supply and income

- Poor availability of crushers- tales of 600 miles to crush seeds

- Low interest loan program to build facilities

- Transport raw products across state lines can violate guidelines and quarantines

- Glycerin- Where do we dispose of it?

- Outlaw ethylene glycol to open up uses for glycerin

Renewable Diesel (Ed has a list of challenges specific to Renewable Diesel):

- There are too many links in the feedstock transport chain. Transportation has to happen by truck—which means that there might be three different trucks to do the refining process.

- Not enough feedstock to get to the size of plant that is needed

- Oils are very expensive. Even with subsidy, oil seeds are not competitive with the price of regular diesel. It is equivalent to an $80-85 / barrel for oil.

- Renewable Diesel not included in state and federal definitions

- Supply of H2- change the mode of operation to make ultra low sulphur diesel

- Shifting liability issues- Industry is still recovering from the last time

Algae:

- Funding for research needs to be crop based and focus on:

  - Location

  - Type

  - Technique in growing

  - Technique in processing

- Need access to CO2- which can not be transported well

  - Co – locate with coal fired power plants

- Mercury is a risk with co-location of coal plants

- Significant capital expense

- Phytology is not a developed field

- Production costs are too high

- Venture capital tends to be very proprietary

  - State Universities are good at sharing information

- What happens to by-products? It can take too much energy to take the H20 out of algae.

Recommendations: The team discussed two separate sets of recommendations. The first set was recommendations that need to be forwarded to the Advisory Committee almost immediately if they are to be relevant (such as the Farm Bill which is being considered by Congress in the very near term). The second set was the recommendations that will help biofuels overcome barriers to achieve full market penetration. The team will need to weed out recommendations that are not actionable by governors.

Short Term Recommendations: The team discussed the Governors’ Ethanol Coalition report and recommendations. It was agreed that the report serves as a good basis for recommendations by WGA governors. There is a very strong geographic overlap and the GEC has had an exhaustive process in developing the recommendations.

Farm Bill

- Subsidize oil seeds going into production – Title I

- Bring back cotton seed support and broaden it to other oil seed crops

- Reallocate funding from the commodity program that is freed up by high corn prices (Governors’ Ethanol Coalition)

- Implement programs in the EPAct that have not been funded

- Use USDA to study crop rotations- Brasicas and how they fit in

- Build better knowledge on continuous cropping and how growers can implement new techniques

- Need funding for research, direct payment or subsidy of crops, and to encourage new practices

- Renewable energy standard of 5% for energy crops (perhaps for a “we the undersigned letter”)

- Add Algae to the list of farm commodity – IRS ruling?

- Facility loan guarantee and low interest loans- for construction of biodiesel production facilities, with education for the government decision-makers to allow the loans to be approved

Report Recommendations: Some of the short-term recommendations may also be included in the report. The report should focus on actions that can be taken by the governors at the state, regional and federal level. Many of the actions discussed at the meeting were state issues which open up many possibilities for effect through this WGA initiative. The major points of the discussion are listed below:

- Develop a better system for labeling and testing that will include:

- NIST = ASTM standards

- Appropriate funding levels to establish and maintain the system

- Protocols to establish greater certainty and methodological integrity

- Testing can be concentrated at the state level

- B-5 Testing

- D-975

- Encourage ASTM to pass B-20 Standard

- Increase funding to do research

- Design a process to build consensus

- ASTM includes producers, users and general interests. Get the states to go and vote as part of the “general interest category”, the states could represent a significant block if they stuck together

- To help rationalize feedstock supply and transport, develop siting guidance for plants, similar to what NREL has done with wind

- Increase production of oil see by:

- Increasing resources for land grant universities, state departments of agriculture

- Include oil seed in commodity price support program. Price support should move from other crops to support the goal of energy independence

- Fund extensions to promote government understanding of a greater diversity of crops as well as programs for farmers

- Develop a risk management strategy possibly through federal insurance

- Use surplus acres (CRP) to produce oil seed crops and energy crops

- Address quality variability through local branding that will reward high quality and discourage imports from outside the US and palm oil

- Include renewable diesel in definitions with the EPA and at the state level, governors should designate a lead agency and define renewable diesel.

- Algae- Funding for multi-university research and R&D

  - In different climates

  - With educational outreach

  - Links resources to labs and universities

  - ID power plants where co-location can work

  - Study the potential for carbon sequestration credits

- Include algae biodiesel as part of RPS eligibility

- Promote use of propylene glycol as made from glycerin

- States and feds should only buy sustainably made propylene glycol for their motor pools

- State motorpool purchases should be ethanol or biodiesel vehicles

- Mandate a renewable fuel standard (OR, WA, ID, MT, NM are all close to or with RFS)

- Deny Production Tax Credit to made from feedstock from outside the US