## WORK PLAN
WESTERN GOVERNORS' ASSOCIATION - Forest Health Advisory Committee Work Plan 12/2010
SUBCOM NAME - OBJECTIVE | PRIORITIES (Bold indicates highest priority) | ACTION ITEMS | DELIVERABLE(S)
LG SCALE TREATMENTS PUBLIC/PRIVATE LANDS
Co-chairs: | Define zones of agreement w/increased collaboration & science | Develop questionnaire/study on successful lg scale pjcts/groups | Completed-study posted on web
Ethan Aumack | Improve planning processes on federal land | Review current natl & state public land policy | Addressed in LST recommendations
Kevin Birch | Identify obstacles to implementing large-scale forest health treatments and the policy changes needed to overcome those obstacles | Synthesize/summarize info from the zones of agreement/collaborative groups study | Completed
|  | Identify obstacles to large-scale treatments and potential policy fixes | Completed
|  | Hold workshop on large-scale treatment policies | Completed
|  | Produce paper on lessons learned | Completed
|  | Submit recommendations to the Governors | Completed
| Develop strategy of where treatments are most needed | Collect and review current science on fuels treatments
CLIMATE CHANGE ADAPTATION (forestland)
Co-chairs: | Trees & Forests Identified in National Policy development | Develop Adaptation strategy to incorporate new technologies/research | Priorities of this subcommittee
Julia Altemus |  | Develop a funding mechanism to achieve goals | will be integrated and addressed by
Crawford Tuttle | Sustain biodiversity in the West | Assess current strategic planning for climate change/adaptation | the Climate Adaptation Work Group
Improve forest resiliency by diversifying forest stands
Promote landscape management and monitoring of biodiversity
| Coordination with Existing Efforts | Identify states with established climate change programs/coordinator
BIOMASS UTILIZATION - BIOENERGY
Co-chairs: | Market Factors (supply & demand) | 1. Support increased removal of merchantable material on federal lands | White paper to WiFLC 7-21-10
Jay O'Laughlin |  | 2. Support permanent authorization for stewardship contracting authorities
Julia Altemus | *Communications (items 3, 4, 5; to some extent are market factors) | 3. Work on biomass definition* | Communication plan in preparation
4. Identify benefits of restoration-based fuel treatments*
5. Talk "triple win" (forest health, renewable energy, revitalized communities)*
|  | 6. Support remedy for bonding/cancellation clause contracting issues | Identified in LST Recommendations
7. Support scaling conversion facilities to sustainable resource supply
8. Support BCAP (Biomass Crop Assistance Program in 2008 Farm Bill)
9. Support access to capital for conversion/retrofits
10. Support incentives for investments in biomass industries
[note: differences in rank between items 2 and 3 are not significant]
[note: differences in rank between items 6 through 10 are not significant]
WILDFIRE PLANS & STRATEGIES
Co-chairs: | Wildland Fire Leadership Council & stakeholders | Increase involvement of stakeholders in WFLC & Cohesive Strategy | Develop recommendations
Carol Daly & Lynn Jungwirth |  | Promote WGA document "Looking Forward" | Develop assessment of CS Ph II & III
| CWPPs and Fire-Adapted Communities | Develop guidance for CWPPs to be included in CS development & implementation | Develop guidance
Promote financial & technical assistance for updating CWPPs to align with CS
Promote public education/prevention; encourage coordination & commo research
| Monitoring, evaluation, reporting, adaptive mgmt | Analyze potential impacts from implementation of CS | Develop report on impacts
Support multi-party monitoring, metrics, & adaptive management of CS

## LG SCALE TX
Large Scale Treatments inclusive of Public/Private lands | LARGE SCALE TREATMENTS - PUBLIC AND PRIVATE LANDS
|  | Aaron Everett | Crawford Tuttle | Maia Enzer/Brady Cullen
|  | Kevin Birch* | Geoff McNaughton | Chuck Burley
|  | Carol Daly | Jeff Jahnke | John Crisp
|  | Sandy Shaffer | Patrick Heffernan | Tom Atzet
|  | Todd Schulke | George Bacon | Gordon Cruikshank
|  | Chuck Bushey | Ryan Yates | Ray Sowers
|  | John Mankowski | Ethan Aumack* | Laura McCarthy

## CCA
Climate Change/Adaptation(Forestland Focus)
Maia Enzer
Greg Aplet
Crawford Tuttle*
Ray Sowers
Geoff McNaughton
Tom Atzet
Julia Altemus*
Todd Schulke
Laura McCarthy
Jay O'Laughlin

## BIOMASS
WOODY BIOMASS – SMALL DIAMETER UTILIZATION
| Ray Sowers | Todd Schulke
| Aaron Everett | Rich Harvey
| Jay O'Laughlin* | Crawford Tuttle
| Gordon Cruikshank | Joe Duda
| Tom Atzet | George Bacon
| Patrick Heffernan | Butch Blazer
| Molly Pitts | Ryan Yates
| Julia Altemus* | John Pine
Maia Enzer
Larry Biles

## WPPS
WILDFIRE PROTECTION PLANS AND STRATEGIES
(Formerly the NATIONAL FIRE PLAN – 10 YEAR STRATEGY IMPLEMENTATION PLAN)
Lynn Jungwirth*
Tom Atzet
Carol Daly*
Sandy Shaffer
Chuck Bushey
Greg Aplet
Crawford Tuttle
Julia Altemus
Thomas Sisk