Partners in Fire Education (PIFE) 		STATUS REPORT

April, 2009

The Partners in Fire Education task group is chartered under the Wildland Fire Leadership Council to collaboratively accomplish the 10-Year Comprehensive Strategy Implementation Plan Task 3A-2.  PIFE provides a bridge between WFLC and NWCG to assist the implementation and accomplishment of this task.  PIFE will continue to work with WFLC and NWCG members through the approval of PIFE developed products.  The group charter, strategic action plan, and developed products will be available on the Western Governors’ Association website.  Once products are approved, they will also reside on the NWCG website.

This task group has been meeting since February 18, 2009 under the guidance of an Executive Committee consisting of representation from the US Forest Service, Department of the Interior, and the Western Governors’ Association.

The joint Steering and Executive committee members are listed below.

- Kate D’Ambrosio, Forest Service-Special Assistant to the Committee

- Jim Erickson, Intertribal Timber Council

- Mike Ferris, Forest Service

- Nancy Guerrero, DOI

- Larry Lesko, Forest Service

- Cathy Sparks, National Association of State Foresters

- Laura McCarthy, The Nature Conservancy

- Becky Denlinger, International Association of Fire Chiefs

- Don Smurthwaite, National Wildland Fire Coordinating Group

- Ann Walker, Western Governors’ Association

Current Developments:

- PIFE charter and Strategic Action Plan are available on the WGA website

- Review and modifications are progressing on the PIFE power point presentation

- Message Triangle is being modified; further efforts will be to finalize this tool

- Peer review of draft messages is scheduled for late April

- PIFE Status Report presentation scheduled for June NWCG meeting and next scheduled WFLC meeting

Charter and Strategic Plan Action Items:

- Draft a PIFE Strategic Action Plan.

  - Completed April, 2009.

- Develop PIFE status update for use at meetings such as NWCG and WFLC meetings

  - Ongoing

- Post status reports, group charter, Strategic Plan, and developed products on the WGA website.

  - Strategic Action Plan, charter and a power point presentation on results of the PIFE study are currently posted.

- Communicate the progress and accomplishments of the PIFE group to internal and external organizations, such as WiFLC, NWCG, etc.

  - Ongoing

- Draft key messages for use by fire community and public audiences to educate communities about their relationship with wildfire and fire’s ecological role.  Two versions of these messages will be necessary:  one set for during fire season, and one for outside fire season.

  - Draft messages have been developed and are being peer reviewed.

- Develop draft message delivery “cheat-sheets”; one for during and one for outside fire season

  - Draft “cheat-sheet” has been developed.

- Re-draft the “message triangle” based on group discussion and consensus

  - Message triangle has been edited to replace “cost effectiveness” with “effectiveness” in brackets

- Discuss and consider use of social media in distribution of PIFE messages

- Integrate messages to the extent possible with those being produced by other groups/agencies

- Seek additional human and financial resources to further PIFE efforts

- Develop recommendations for future PIFE messages and potential products should additional human and financial resources become available

- Discuss future considerations of expanding PIFE messages to touch on key issues such as personal responsibility, climate change, biomass utilization, forest health, cultural differences in reactions and perceptions of wildfire.

  - PIFE is exploring JFSP research funding.

For more information, please contact a PIFE charter member.

- Jim Erickson, Intertribal Timber Council Jim.Erickson@couleedam.net

- Mike Ferris, Forest Service mferris@fs.fed.us

- Nancy Guerrero, DOI Nancy_Guerrero@ios.doi.gov

- Larry Lesko, Forest Service llesko@fs.fed.us

- Cathy Sparks, National Association of State Foresters catherine.sparks@dem.ri.gov

- Laura McCarthy, The Nature Conservancy lmccarthy@tnc.org

- Becky Denlinger, International Association of Fire Chiefs Becky.Denlinger@gov.bc.ca

- Don Smurthwaite, National Wildland Fire Coordinating Group Don_Smurthwaite@nifc.blm.gov

- Ann Walker, Western Governors’ Association awalker@westgov.org

Partners in Fire Education

April, 2009