## Color
WESTERN RENEWABLE ENERGY ZONE: GOVERNANCE AND STAKEHOLDER PARTICIPATION | [16 empty] | Legend (Status of Task)
May 2008 | [14 empty] | In Progress |  |  | Complete |  |  |  | Event Week
[15 empty] | Once a month |  |  | Once a week
Dates | [14 empty] | Twice a month
| 2008 | [31 empty] | 2009
| May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January
Week | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Tasks
Form & Organize Steering Committee
SC Meeting
Convene Technical Committee
Form "REZ" Workgroup and develop criteria for REZs
Form other Workgroups [meet weekly by phone]
Technical Committee Calls
wg one more in person meeting [ahead of TC -- dft products -- sept]
WG products to TC | [12 empty] | dft | dft
CC briefings for public/web exchange for public/other communication
In-person Technical Committee Meeting Sept/November
Stakeholder Meetings Oct/Nov
Steering Committee Adoption of Technical Committee Products [conf call briefings]
SC/TEC Stakeholder Meeting December